## Resource Assigment
Resource Name | Organization | Location | Skill Group | Skillset | Level | Project Name | Resource Planned Start Date | Resource Planned Finish Date | Planned Hours
Advani, Gul | BMCX | Noida | Java | ObjectiveC, Swift | Senior | NO Project Assigned | NULL | NULL | 0
Agrawal, Ekta | INS | Pune | Web | ObjectiveC, Swift | Senior | BCN – Vitria Retirement P | 2018-01-22 | 2018-07-18 | 1024
Aluri, Sailaja | EXT | Noida | Java | ObjectiveC, Swift | Middle | Lochbridge Non-Billable A | 2018-01-01 | 2018-05-04 | 450
Ball, William | INS | Barcelona | .NET | ObjectiveC, Swift | Middle | Key Bank Mobile UAP Perfo | 2018-01-01 | 2018-08-15 | 1100
Barnum, Charles | INTL | Barcelona | Xamarin | ObjectiveC, Swift | Senior | Cochrane Building Control | 2018-01-22 | 2018-09-09 | 800
Chandrasekaran, Dinesh | INTL | Detroit | Web | ObjectiveC, Swift | Junior | BCN - LIMP Phase II | 2017-12-01 | 2018-07-12 | 1200
Chugh, Aashish | INS | Detroit | Xamarin | ObjectiveC, Swift | Senior | Training | 2018-01-01 | 2018-07-30 | 1600
Dhullipala Chenchu, Ravi | BMCX | Detroit | Architect | ObjectiveC, Swift | Junior | OnStar Allegis - Dilli - | 2017-11-01 | 2018-03-29 | 856
DuBay, Philip | INS | Barcelona | Android | ObjectiveC, Swift | Senior | GM Web Ops. Analyst - PRJ | 2017-11-01 | 2018-10-21 | 2000
Ganesan, Hariharan | BMCX | Barcelona | iOS | ObjectiveC, Swift | Senior | PSD104 ALLEGIS SPECIAL TM | 2018-01-20 | 2018-07-29 | 900
Gummadi, Shalini | EXT | Pune | .NET | ObjectiveC, Swift | Middle | Lansing Board of Water an | 2017-11-01 | 2018-07-24 | 1300
Halapeth, Milind | EXT | Noida | .NET | ObjectiveC, Swift | Middle | NO Project Assigned | NULL | NULL | 0
Heminger, Charles | EXT | Noida | .NET | ObjectiveC, Swift | Junior | NO Project Assigned | NULL | NULL | 0
Hershberger, Mark | BMCX | Detroit | Architect | ObjectiveC, Swift | Senior | VW Canada - CASL Implemen | 2017-12-01 | 2018-11-12 | 1670
Hillegonds, Mark | EXT | Noida | Java | ObjectiveC, Swift | Junior | Volkswagen Group Canada - | 2018-01-01 | 2018-08-22 | 1234
Horwitz, Daniel | BMCX - EXT | Noida | Architect | ObjectiveC, Swift | Junior | Recruiting Non-Billable A | 2017-11-01 | 2018-02-24 | 456
Horwitz, Daniel | BMCX - EXT | Noida | Architect | ObjectiveC, Swift | Junior | OnStar GCCX App Ecosystem | 2017-09-01 | 2018-02-24 | 1008
Iverson, Christopher | BMCX - EXT | Detroit | Web | ObjectiveC, Swift | Senior | Public Sector Sales Work | 2018-02-12 | 2018-06-19 | 674
Jacob, Wilson | BMCX | Detroit | iOS | ObjectiveC, Swift | Junior | No Project Assigned | NULL | NULL | 0
Jakilepi, Renuka | EXT | Barcelona | Web | ObjectiveC, Swift | Senior | CFNA LM2 TERMS Change (AI | 2017-11-01 | 2018-11-03 | 1800
Jakilepi, Renuka | EXT | Barcelona | Web | ObjectiveC, Swift | Senior | GM Web Ops. Analyst - PRJ | 2017-11-01 | 2018-11-03 | 1700
Jalligampala, Deepak | INTL | Noida | .NET | ObjectiveC, Swift | Junior | No Project Assigned | NULL | NULL | 0
Johnson, Eric | EXT | Barcelona | Architect | ObjectiveC, Swift | Middle | SPECIAL - GSSM - BEELINE | 2017-01-17 | 2017-09-24 | 778
Kadiyala, Madhuri | BMCX - EXT | Detroit | iOS | ObjectiveC, Swift | Junior | No Project Assigned | NULL | NULL | 0
Kakumanu, Suresh | BMCX | Pune | Xamarin | ObjectiveC, Swift | Middle | VW Canada - CASL Implemen | 2018-01-01 | 2018-07-30 | 1208
Kennedy, Pamela | BMCX | Pune | Web | ObjectiveC, Swift | Junior | ROCKWELL PROJECT CONCORD | 2017-11-01 | 2018-08-28 | 1720
Kline, Eris | EXT | Noida | Xamarin | ObjectiveC, Swift | Senior | BCN - Vitria Retirement | 2018-01-22 | 2018-09-19 | 1384
Kumar, Girish | INS | Detroit | Java | ObjectiveC, Swift | Middle | NO Project Assigned | NULL | NULL | 0
Kypros, Sharon | BMCX | Detroit | Android | ObjectiveC, Swift | Junior | ONSTAR FACTORY DOWNTIME 1 | 2017-01-17 | 2017-11-13 | 1400
Leibo, Gary | BMCX - EXT | Barcelona | Java | ObjectiveC, Swift | Junior | Commercial Sales Work | 2017-12-01 | 2018-04-25 | 832
Lorcencov, Alexandr | BMCX - EXT | Pune | Architect | ObjectiveC, Swift | Middle | NO Project Assigned | NULL | NULL | 0
Maldoddi, Laxmikanth | INTL | Detroit | Web | ObjectiveC, Swift | Senior | Volkswagen Audi Owners Ma | 2018-01-01 | 2018-06-06 | 800
Marenda, Joan | INS | Detroit | Android | ObjectiveC, Swift | Junior | Volkswagen Group of Ameri | 2018-01-22 | 2018-08-23 | 1000
Marri, Shilpa | INS | Pune | iOS | ObjectiveC, Swift | Middle | BCBS-VAS ASSIGNMENT 22029 | 2018-01-22 | 2018-06-21 | 668
Nidamanuri, Sai Siva Prasad | EXT | Barcelona | iOS | ObjectiveC, Swift | Middle | Finance and Insurance Sal | 2018-01-01 | 2019-01-03 | 2112
Njunjic, Ivan | INTL | Pune | Android | ObjectiveC, Swift | Senior | APP. FACTORY SERVICES 210 | 2018-01-22 | 2018-07-11 | 900
Noland, Jeffrey | INS | Barcelona | Architect | ObjectiveC, Swift | Senior | Volkswagen Real-TimeIncen | 2018-01-01 | 2018-07-30 | 800
Osborn, Kathleen | INTL | Barcelona | .NET | ObjectiveC, Swift | Senior | BCN - LIMP Phase 5 | 2017-11-01 | 2019-01-17 | 2100
Panchal, Jan | BMCX - EXT | Pune | Web | ObjectiveC, Swift | Middle | Practice - Program and Pr | 2017-11-01 | 2018-09-07 | 1700
Peters, Robin | EXT | Noida | iOS | ObjectiveC, Swift | Middle | BCBSM - Kypros 2015 | 2018-01-17 | 2018-04-27 | 584
Sahu, Tridibesh | INTL | Noida | Architect | ObjectiveC, Swift | Senior | Healthcare - NB - Beaumon | 2018-01-01 | 2018-05-04 | 720
Sambhara, Sowmya | INTL | Noida | Android | ObjectiveC, Swift | Junior | No project Assigned | NULL | NULL | 0
Schackor, Laura | EXT | Detroit | Xamarin | ObjectiveC, Swift | Junior | Beaumont Health - Web Ass | 2018-01-01 | 2018-05-04 | 720
Smith, Angie | INTL | Detroit | Xamarin | ObjectiveC, Swift | Middle | OnStar Infotainment and R | 2017-11-01 | 2018-04-15 | 944
Smith, Angie | INTL | Detroit | Xamarin | ObjectiveC, Swift | Middle | Covisint - Auto OnStar Po | 2017-11-01 | 2018-05-18 | 1000
Smith, Angie | INTL | Detroit | Xamarin | ObjectiveC, Swift | Middle | GM Web Ops. Analyst - PRJ | 2017-11-08 | 2018-09-18 | 1500
Story, Theodore | BMCX | Pune | Xamarin | ObjectiveC, Swift | Middle | BCN - LIMP Phase 4 | 2017-11-01 | 2018-07-15 | 978
Subbaiah, Manjunatha | INTL | Detroit | Xamarin | ObjectiveC, Swift | Middle | Covisint - Auto OnStar Po | 2017-11-01 | 2018-03-05 | 712
Sullivan, David | BMCX | Detroit | Web | ObjectiveC, Swift | Middle | CGI BUSINESS ANALYST 2013 | 2017-01-01 | 2017-07-30 | 1200
Sullivan, David | BMCX | Detroit | Web | ObjectiveC, Swift | Middle | OnStar GCCX App Ecosystem | 2017-04-20 | 2017-07-30 | 576
Suryadevara, Narma | BMCX | Noida | Android | ObjectiveC, Swift | Senior | BCN - LIMP Phase 3 | 2017-12-01 | 2018-05-18 | 968
Talluri, Bhavya | BMCX - EXT | Pune | Android | ObjectiveC, Swift | Senior | PC - Internal Project | 2018-01-01 | 2018-09-29 | 1560
Taylor, Kandace | BMCX - EXT | Detroit | Java | ObjectiveC, Swift | Senior | Automotive Sales Work | 2017-12-01 | 2018-06-29 | 1208
Terrien, Jane | EXT | Noida | iOS | ObjectiveC, Swift | Middle | Healthcare Sales Work | 2018-02-12 | 2018-10-15 | 1408